## Risk Tracking Template
Project Risk, Impact, Risk level
Date of last review: |  | 16.04.2024
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Supplier delay | Pushes launch | Confirm delivery dates by Phase 2 | High | Richi | SAMPLE
2 | Food shortage | Reduces efficiency in waste processing. | Adjusting processing schedules. | Low | Richi | SAMPLE
3 | Data Security and Privacy | Compromises customer information leading to identity theft or fraud | Implementing encryption protocols for sensitive data transmission | High | Jarif, Ashfaq and Eishita | SAMPLE
4 | Food Contamination | Public health crises. | Implementing strict sanitation protocols and regular monitoring of food handling processes. | High | Jarif | SAMPLE
5 | Software integration challenges | Disruptes workflow efficiency. | Conducting thorough compatibility testing before implementation. | Low | Ashfaq | SAMPLE
6 | Implement feedback mechanism | Continuous refinement and imrovement of system based | Heavily relies on gathering | Low | Eishita | SAMPLE
7 | Volunteer management | Ensure edequte training and supervirsion of volunteers | Develop emergency respons plans and communication protocols | High | Jarif, Ashfaq and Eishita | SAMPLE
8 | Software obsolescence, compatibility issues | Technological obsolescence | Regular Software Updates and Maintenance,User Training and Support | Low | Eishita | SAMPLE
9 | Exceed the project budget | Cost Overruns | Regular Budget Monitoring,Stakeholder Communication | High | Eishita | SAMPLE

## How to Use this Template
Introduction
A risk tracking template allows you to identify and track any risks that might appear in your project. It's critical to track risks in your projects, so they don't become issues that derail progress. A risk tracking template is a living document, and should be frequently inspected and updated.
Definition of Terms
ID: The identification number of your risk.
Description of Risk: Provide a brief description of your risk that anyone can understand.
Impact: Outline the potential impact that risk can have on your project.
Risk Response: Describe what your reaction to the risk is, in order to quell it.
Risk Level: Define the priority of the risk; how likely it is to affect your project.
Risk Owner: Define the team member or manager in charge of monitoring the risk.
Notes: Add any notes you may have for a better understanding of the risk. Update regularly.